The Philippines ICSF Project

Outcome:

The SSF Guidelines are integrated into policies and laws governing the small-scale fisheries sector at the national level.

Activities:

- Compilation and review of major policies and laws governing the small-scale fisheries subsector in the Philippines

- Benchmarking of the Philippine policies and laws governing small-scale fisheries with the SSF Guidelines components

- Compilation and review of existing fisheries programmes and policies related to natural disasters and climate change

- Consultation with government agencies engaged in the SSF subsector

- Consultation with major stakeholders on identifying challenges to participation in food security and poverty eradication

- Development of strategies towards implementation of the SSF Guidelines in the Philippines

- Consultation workshops with government agencies on mainstreaming of the SSF Guidelines towards greater participation of small-scale fishers in food security and poverty eradication

- Capacity building for national and local implementers of the SSF Guidelines

- Identify strategies for advocacy and implementation of the SSF Guidelines at the national level

- Targeted information, education and communication (IEC) for key government agencies engaged in the implementation of policies and programmes governing the SSF sector

1.3 Workplan and Timeframe (Duration)

The project will be completed over a period of a maximum of eleven months, after signature of the present Agreement by both parties, as indicated below:

| Expected activities | Required completion date | Status |
| --- | --- | --- |
| 1) Country level activities initiated in your country | 30-Sep-18 |  |
| 2) Country level activities concluded in your country | 30-Mar-19 |  |
| 3) Country reports prepared |  |  |
| 4) Final report prepared and submitted in word format to ICSF for submission to FAO | 31-May-19 |  |
| 5) Final Financial report prepared and submitted to ICSF in Excel format for submission to FAO with soft copy of all outputs | 30-Jun-19 |  |

2.3a. Work plan and Time Frame

(the service provider has to fill this plan by using a tick  mark indicating the duration of the activity. Please keep the non activity months as blank. ). This will be done by the service provider on or before 30 September 2018, subject to approval and on which the second installment will be released.

| Activity | Timeplan | Status |
| --- | --- | --- |
|  | 2018 | 2019 |  |
|  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul |  |
| Compilation and review of major policies and laws governing the small-scale fisheries subsector in the Philippines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Benchmarking of the Philippine policies and laws governing small-scale fisheries with the SSF Guidelines components |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Compilation and review of existing fisheries programmes and policies related to natural disasters and climate change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Consultation with government agencies engaged in the SSF subsector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Consultation with major stakeholders on identifying challenges to participation in food security and poverty eradication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of strategies towards implementation of the SSF Guidelines in the Philippines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Consultation workshops with government agencies on mainstreaming of the SSF Guidelines towards greater participation of small-scale fishers in food security and poverty eradication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capacity building for national and local implementers of the SSF Guidelines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify strategies for advocacy and implementation of the SSF Guidelines at the national level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Targeted information, education and communication (IEC) for key government agencies engaged in the implementation of policies and programmes governing the SSF sector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

2.3 b. Performance indicators and means of verification

| Activity | Indicator | Means of verification | Status |
| --- | --- | --- | --- |
| Compilation and review of major policies and laws governing the small-scale fisheries subsector in the Philippines | Experience of the person preparing the review paper ToR for the review Contents and coverage of the review paper from the angle of major policies and laws governing the small-scale fisheries subsector | Progress report to indicate the profile the person doing the review and the ToR Detailed review report on major policies and laws governing the small-scale fisheries subsector in the Philippines |  |
| Benchmarking of the Philippine policies and laws governing small-scale fisheries with the SSF Guidelines components | Experience of the person doing the bench marking ToR for the bench marking Contents and coverage of the Benchmarking of the Philippine policies and laws governing small-scale fisheries with the SSF Guidelines components | Progress reeport to indicate the profile the person doing the review and the ToR Detailed report on Benchmarking of the Philippine policies and laws governing small-scale fisheries with the SSF Guidelines component |  |
| Compilation and review of existing fisheries programmes and policies related to natural disasters and climate change | Experience of the person doing the compilation and review ToR for the compilation and review Contents and coverage of the Compilation and review of existing fisheries programmes and policies related to natural disasters and climate change | Progress report to indicate the profile the person doing the review and the ToR Detailed report on Compilation and review of existing fisheries programmes and policies related to natural disasters and climate change |  |
| Consultation with government agencies engaged in the SSF subsector | Details of the agencies and the consultations held as well as the outcome. | Progress report to mention the work progress Report on the consultation with government agencies engaged in the SSF subsector |  |
| Consultation with major stakeholders on identifying challenges to participation in food security and poverty eradication | Details of the stake holders involved and the consultations held as well as the outcome.. | Progress report to mention the work progress Report on the consultation with major stakeholders on identifying challenges to participation in food security and poverty eradication |  |
| Development of strategies towards implementation of the SSF Guidelines in the Philippines | Process followed for the developing the strategy Recommendations made on strategies for implementation of the SSF Guidelines in the Philippines | Progress report Report on strategies towards implementation of the SSF Guidelines in the Philippines |  |
| Consultation workshops with government agencies on mainstreaming of the SSF Guidelines towards greater participation of small-scale fishers in food security and poverty eradication | Plan and participant proposed for the workshops Actual participation, agenda, process and outcome of the workshops | Progress report Detailed report on workshops with government agencies on mainstreaming of the SSF Guidelines towards greater participation of small-scale fishers in food security and poverty eradication |  |
| Capacity building for national and local implementers of the SSF Guidelines | Process contents, participation and outcome of the capacity building | Progress report Detailed report on capacity building for national and local implementers of the SSF Guidelines |  |
| Identify strategies for advocacy and implementation of the SSF Guidelines at the national level | Process followed for the identifying the strategy Recommendations made on strategies for advocacy and implementation of the SSF Guidelines at the national level | Progress report Report on strategies for advocacy and implementation of the SSF Guidelines at the national level |  |
| Targeted information, education and communication (IEC) for key government agencies engaged in the implementation of policies and programmes governing the SSF sector | Contents and details of the IEC material prepared as per the target audience Actual IEC material in print or video format and its distribution/ dissemination | Progress report The IEC material produced for key government agencies engaged in the implementation of policies and programmes governing the SSF sector |  |

2.4 Monitoring Mechanisms and Reporting Requirements

- Quarterly Progress report received electronically in word format in English that specifies for country-level activity showing the current status of implementation, key next steps, highlights, any delays or challenges incurred and spells out any need for modification (if any) On 5 Nov 2018,5 Feb 2019 and 5 Jun 2019. Have you submitted the report?.

- Interim reports as highlighted in the means of verification under 2.3b above. Please mention the status?