

**BR007**

**Performance indicators and means of verification**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Activity** | **Indicators** | **Means of verification** | **Progress and results of activities** | **Status indicators** | **File Reference** |
| 1.Preparatory meeting in Manaus (Amazonas State) with Brazilian organizations with a track-record of working with indigenous groups | * Process followed for organizing and during the meeting
* Participants in the meeting
* Discussions relevant to indigenous people among SSF
 | * Progress report
* **Report on preparatory meeting in Manaus**
 | * Detailed report ready and delivery
* Result: Initial planning of the Seminar ready, such as date, lodging, meals, guest list and Seminar programming
 | * Achieved
 | BR001 |
| Organization of the Workshop | * Agenda and participants including group photograph
* Participation of relevant stakeholdrs including human rights Commission
* Process followed and out put of the workshop
 | * Progress report
* **Detailed Workshop report**
* Representatives of local, provincial and federal government
 | * Workshop took place on March 27 and 28
* Broad participation of indigenous people, representing 17 ethnic groups, and local and federal government entities
* Results: Indigenous people from 17 ethnic groups from the state of Amazonas, NGOs and governmental entities from the state of Amazonas became aware of the Guidelines; partici-

pants exchanged experiences and contacts to initiate community-based tourism and fisheries management projects in their respective Indigenous Lands; family aquaculture project established between interested indigenous people, university and FUNAI | * Achieved
 | BR002 |
| Preparation of a synthesis document to be discussed during the Workshop on main issues of concern and policy measures of interest to indigenous groups based on SSF Guidelines | * Experience of the person doing the synthesis paper
* ToR for the synthesis paper
* Contents for the synthesis paper
 | Progress report indicating* CV of the person and the ToR for preparation of the synthesis paper
* **Synthesis document of main issues of fisheries and indigenous people**
* **Proposed agenda and participants for the workshop**
 | * CV, ToR, Synthesis paper, Proposed agenda and participants for the workshop ready e delivery
* Result: closure of the Seminar schedule. Written part of the workshop preparatory material is ready
* Next step: Definition and purchase of tickets. Art and layout of folders
 | * Achieved
 | BR003 |
| Production of audio/visual material covering the workshop proceedings  | * Coverage of the audio visual material
 | * Progress report
* **Video document**

(link to the video is in the video document word file) | * Material audio\visual ready and delivery
* Result: Video subtitled in English covering the event and containing interviews of participants
 | * Achieved
 | BR004 |
| Final report of proceedings and a synthesis document to update the Vital Fisheries strategy | * Agenda and participants including group photograph
* Process followed and out put of the workshop
* Points and processes in synthesis with regard to a vital fishery strategy in favour of the indigenous groups among SSF
 | * Progress report
* **Country Report**
 | * Detailed report ready and delivery
* Result: Final report containing all working group discussions and information on the main basins of the State of Amazonas, as well as the ethnic groups living in each basin \ river, land demarcations, protected areas, conflicts and fisheries-related problems of the indigenous peoples of the region
 | * Achieved
 | BR005 |