Indonesia: Study work plan by Dedi Adhuri

Outcome:

Improved awareness of the State about securing customary institutions and strengthening the rights of women to enhance fisheries governance, food security and poverty reduction of local and traditional communities in their fishing grounds and adjacent land in selected islands of the Indonesian archipelago.

Activities:

- Prepare a paper on how Law No. 1/2014 and Law No. 7/2016 could apply the SSF Guidelines to secure the tenure rights to conservation and sustainable use of marine and coastal resources of customary, local and traditional fishing communities as well as to the resources that form the basis of their social and cultural well-being, their livelihoods and their sustainable development. The paper will also look at how to protect and empower these communities and their families (especially, under Law No. 7/2016) in light of the SSF Guidelines. The paper will be in the form of a draft action plan.

1.3 Workp1an and Timeframe (Duration)

The project will be completed over a period of a maximum of eleven months, after signature of the present Agreement by both parties, as indicated below:

| Expected activities | Required completion date |
| --- | --- |
| 1) Country level activities initiated in your country | 30 September 2018 |
| 2) Country level activities concluded in your country | 30 March 2019 |
| 3) Country reports prepared | 30 April 2019 |
| 4) Final report prepared and submitted in word format to ICSF for submission to FAO | 31 May 2019 |
| 5) Final Financial report prepared and submitted to ICSF in Excel format for submission to FAO with soft copy of all outputs | 30 June 2019 |

2.3 a. Work plan and Time Frame (the service provider has to fill this plan by using a tick (mark indicating the duration of the activity. Please keep the non activity months as blank. ). This will be done by the service provider on or before 30 September 2018, subject to approval and on which the second installment will be released.

| S.No. | Activity | Time Plan |
| --- | --- | --- |
|  |  |  | 2018 | 2019 |
|  |  | Detail Activity | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Detail |
| 1 | Prepare a paper on how Law No. 1/2014 and Law No. 7/2016 could apply the SSF Guidelines to secure the tenure rights to conservation and sustainable use of marine and coastal resources of customary, local and traditional fishing communities as well as to the resources that form the basis of their social and cultural well-being, their livelihoods and their sustainable development. The paper will also look at how to protect and empower these communities and their families (especially, under Law No. 7/2016) in light of the SSF Guidelines. The paper will be in the form of a draft action plan |  |  |  |  |  |  |  |  |  |  |  |  |  |

2.3 b. Performance indicators and means of verification

| Activity | Indicator | Means of verification |
| --- | --- | --- |
| Prepare a paper on how Law No. 1/2014 and Law No. 7/2016 could apply the SSF Guidelines to secure the tenure rights to conservation and sustainable use of marine and coastal resources of customary, local and traditional fishing communities as well as to the resources that form the basis of their social and cultural well-being, their livelihoods and their Sustainable development. The paper will also look at how to protect and empower these communities and their families (especially, under Law No. 7/2016) in light of the SSF Guidelines. The paper will be in the form of a draft action plan | Experience of the person preparing the paper ToR for the paper preparation Contents and coverage of the paper from the angle of looking at law 1//2014 and 7/2016 from the SSF angle as per the ToR | Progress report Detailed study report on applying Law No. 1/2014 and Law No.7/2016 from the point of implementing the SSF guidelines |

2.4 Monitoring Mechanisms and Reporting Requirements

- Quarterly Progress report received electronically in word format in English that specifies for country-level activity showing the current status of implementation, key next steps, highlights, any delays or challenges incurred and spells out any need for modification (if any) On 5 Nov 2018,5 Feb 2019 and 5 Jun 2019. Have you submitted the report?.

- Interim reports as highlighted in the means of verification under 2.3b above. Please mention the status?